WyreStorm Wingman

Action Plan to Complete Features & Reach Production

Prepared for Steve Goodwin  •  6 June 2026  •  Status: Late-stage / Pre-launch

# Contents

# 1. Executive Summary

Wingman is much further along than earlier project notes implied. The codebase is a mature React/TypeScript front end (149 source files, 30+ pages) with a Node back end, a 187-product intelligence database, Docker, CI/CD, an error boundary, a unit-test suite, configurable security, and a Supabase storage path. TypeScript type-checking passes clean and the project's own readiness check reports all canonical data and workflow wiring verified.

In short: the heavy infrastructure lifting described in the older deployment plan is largely complete. The remaining work is consolidation rather than construction — finishing a handful of features to the standard set out in the product rules, proving the whole verification suite stays green, provisioning and migrating to production storage, a final security pass, and a controlled launch backed by a workshop soak-test.

Realistic time to a customer-facing launch: 2–3 focused weeks, assuming production hosting and a Supabase project are made available early.

## Current readiness snapshot

| Area | State | Notes |
| --- | --- | --- |
| Front-end UI / pages | Strong | 30+ pages render; IntelligencePage now fully implemented (was previously null). |
| Build & type safety | Green | tsc type-check passes; Vite build wired into verify gate. |
| Automated tests | Partial | 5 unit suites exist; no end-to-end suite yet; runner needs confirming on your machine. |
| Product-selection logic | Needs proof | Engine exists; must demonstrate it obeys the domain rules (variety, EXP guardrail). |
| Back-end services | Good | Auth, RBAC, rate limiting, agent + competitor APIs present. |
| Production storage | Coded, not provisioned | Supabase mode + schema migration exist; no live project / data migration yet. |
| Security | Good foundation | Secure cookies & CORS now env-configurable; CSRF + secrets management outstanding. |
| Deployment infra | Built | Dockerfiles, docker-compose, CI + Docker workflows, DEPLOYMENT.md all present. |
| Repo hygiene | Cleanup needed | 25 .bak files committed under src/, including duplicate page backups. |

# 2. Already Done — Do Not Redo

These items from the earlier readiness plan are now complete in the repository. They are listed so effort is not wasted re-solving them:

- Docker + docker-compose for front end and back end, plus .dockerignore.

- GitHub Actions CI (ci.yml) and Docker build (docker.yml) workflows.

- React ErrorBoundary component, wired into the app shell in main.tsx.

- Unit-test scaffold with suites for the project store, document extraction, competitor match engine, recommendation evidence and the error boundary.

- IntelligencePage rebuilt — no longer returns null; full product-intelligence admin view.

- Session cookies default to Secure in production; CORS origin configurable via WINGMAN_CORS_ALLOW_ORIGIN with a production wildcard guard.

- Supabase storage mode with fail-closed behaviour and an initial schema migration (001_initial_schema.sql).

- DEPLOYMENT.md, load-testing harness, and an extensive self-check suite (npm run verify runs 25+ guards).

# 3. The Plan at a Glance

Work is grouped into six phases. A and D are the launch-critical path; B and C raise quality and finish the headline features; E and F harden and ship.

| Phase | Focus | Outcome | Effort |
| --- | --- | --- | --- |
| A | Stabilise & prove green build | Clean repo, full verify suite passes, tests run | 2–3 days |
| B | Data & selection accuracy | Product picks obey the domain rules | 3–4 days |
| C | Feature completion | GURU, Compare, Proposal/diagrams finished | 4–6 days |
| D | Production infrastructure | Supabase live, secrets, monitoring, hosting | 3–4 days |
| E | Security & compliance | CSRF, secret rotation, security review | 2 days |
| F | Launch | Soap-test workshop, UAT, go/no-go | 2–3 days |

# 4. Phase A — Stabilise & Prove a Green Build

Goal: a clean repository where one command (npm run verify) passes end to end, and the test runner works on your machine. This is the safety net everything else relies on.

### Tasks

- Remove the 25 committed .bak files under src/ (including duplicate page backups such as IntelligencePage, ProposalPage, TemplatesPage, ProductPitchPage) and add a *.bak ignore rule so they never re-commit.

- Run the full npm run verify gate and fix anything that fails so it goes green end to end (typecheck already passes; confirm build + all 25 checks).

- Confirm the unit-test suite (npm run test) runs cleanly on your Windows machine — a native module error appeared in the sandbox and needs ruling out as environment-only.

- Triage React Router v7 future-flag warnings now appearing in the dev log; opt into the future flags to avoid a breaking surprise on upgrade.

- Tag a known-good baseline commit before feature work resumes, so there is a clean rollback point.

Exit criteria: npm run verify green, tests passing, no .bak files in src/, baseline tag created.

# 5. Phase B — Data & Product-Selection Accuracy

Goal: prove the recommendation engine makes correct, varied, rule-compliant product choices. This is the core of Wingman's credibility with sales teams and customers.

### Tasks

- Validate the EXP guardrail: confirm no SKU beginning with EXP is ever proposed as a primary switching device — only for basic signal splitting, HDMI cabling, or a local lectern switch within a larger system.

- Prove selection variety: run varied room scenarios and confirm the engine does not keep defaulting to the same product just because I/O counts look similar; capture evidence in the existing check scripts.

- Verify room-type differentiation: corporate vs education vs government vs hospitality, and size/capacity/multi-screen/IP-vs-cable cases each drive materially different designs.

- Confirm UC product caveats surface in output: WyreStorm UC kit is Zoom-certified but not specifically certified for Microsoft Teams, and Teams MTRs should be tested before install.

- Re-run the product-intelligence index and data-source audits; resolve any UTF-8 / encoding issues in template and product data.

- Spot-check 6–8 representative BOMs end to end for technical accuracy, including 'by others' placeholder rows and signal-path assumptions (distance, voids, cable type, USB bandwidth).

Exit criteria: documented test runs showing rule-compliant, varied, room-appropriate recommendations across all verticals.

# 6. Phase C — Feature Completion

Goal: bring the headline features to a finished, demonstrable standard. Most exist as pages already; this phase is about completing behaviour and polish, not building from scratch. Confirm-then-finish each one.

## GURU knowledge assistant

- Works for both signed-in and guest users, as a working tool and a marketing demo.

- Remove or clearly flag any silent mock-mode fallback so it never quietly returns canned answers in production.

- Handles product, AV term, acronym and system questions, plus call-notes / transcript interpretation.

## Competitor compare

- Honest pros and cons (genuine investigative assessment, not promotional copy).

- Live-lookup match engine returns sensible WyreStorm equivalents with evidence.

- Graceful handling when a competitor SKU can't be resolved.

## Proposal & connectivity diagrams

- Discovery → Proposal flow produces a clean, customer-ready document end to end.

- Connectivity / schematic diagrams generate correctly, including multi-display and IP-vs-cabled infrastructure cases.

- Visual Design Studio and Videowall builder reviewed for completeness and export quality.

## Cross-cutting UI polish

- Form validation extended to all input-heavy pages (Discovery already done).

- Loading skeletons and aria-live for long-running operations; keyboard support for voice capture.

Exit criteria: each headline feature demoable end to end without dev intervention or mock fallbacks.

# 7. Phase D — Production Infrastructure

Goal: move from 'runs on a dev machine' to 'runs reliably for customers'. This phase needs two decisions from you early (hosting and Supabase) — see Section 10.

- Provision a Supabase project (or managed Postgres); apply the existing schema migration.

- Migrate data from the file store to Supabase and verify integrity; keep the file backup.

- Set WINGMAN_STORAGE_MODE=supabase and exercise the app against live storage under concurrent use.

- Move all secrets (Gemini key, Google CSE, Supabase service-role key) into the host's secret manager — never in the repo or a committed .env.

- Stand up health checks, structured logging, and basic monitoring/alerting (uptime + error rate).

- Provision hosting, domain and TLS; run the CI/CD pipeline through to a staging deploy.

- Run the load-testing harness against staging and confirm it holds target concurrency.

Exit criteria: app deployed to staging on production-grade storage, monitored, and load-tested.

# 8. Phase E — Security & Compliance Hardening

- Add CSRF protection for state-changing requests (currently relying on SameSite cookies only).

- Define an API-key rotation procedure and document it in OPERATIONS.md.

- Run a full security review of the production configuration with HTTPS enforced end to end.

- Confirm rate limiting, session management and RBAC behave correctly against staging.

- Decide whether SSO / OAuth is needed for launch or a fast-follow.

Exit criteria: security review passed; no high-severity findings open at launch.

# 9. Phase F — Launch

- Soap-test every standard design in a workshop to confirm real-world interoperability (per the WyreStorm design rule that all designs are workshop-tested before install).

- Run user-acceptance testing with 2–3 salespeople on the full Discovery → Proposal journey.

- Finish operator docs: README polish, DEPLOYMENT.md walkthrough, OPERATIONS.md runbooks, rollback procedure.

- Final full verify + load test on staging; production deploy behind the pipeline.

- Go / no-go review against the success criteria below.

# 10. Decisions Needed From You

These block Phase D and should be settled in week one:

| Decision | Why it matters / options |
| --- | --- |
| Production hosting | Where the app and API run (e.g. a container host, VPS, or cloud platform). Determines deploy target and TLS setup. |
| Database | Confirm Supabase (recommended — already coded) vs self-managed Postgres. Needed before data migration. |
| Auth scope for launch | Email/password only at launch, or add SSO/OAuth? Affects Phase E scope. |
| Gemini / search keys | Confirm production API keys and quotas for GURU and competitor search. |
| Launch audience | Internal sales only first, or external customers? Sets the security/UAT bar. |

# 11. Success Criteria

### Minimum viable launch

- All Phase A items green and stable

- Core Discovery → Proposal flow works end to end

- Product picks pass the rule checks (variety + EXP guardrail)

- Running on Supabase in staging with monitoring

- Security review passed, no high-severity issues

### Full production ready

- End-to-end test suite covering the main journeys

- Load test meets target concurrency

- Soap-test workshop completed for standard designs

- Runbooks tested, rollback rehearsed

- UAT sign-off from sales users

Companion file: WINGMAN_PRODUCTION_TRACKER.xlsx contains every task above as a working checklist with phase, priority, effort and status columns.