## Tracker
WyreStorm Wingman — Production Readiness Tracker
Work through Phase A first (launch safety net), then B–F. Set Status from the dropdown; the Dashboard tab summarises progress.
# | Phase | Task | Priority | Effort (days) | Status | Owner | Notes / acceptance
1 | A | Remove 25 .bak files from src/ and add *.bak to .gitignore | High | 0.5 | Not started |  | Stops duplicate/stale pages being shipped
2 | A | Run full 'npm run verify' and fix until green end to end | High | 1 | Not started |  | Typecheck already passes; confirm build + all 25 guards
3 | A | Confirm 'npm run test' runs on your Windows machine | High | 0.5 | Not started |  | Native-module error seen in sandbox; rule out as env-only
4 | A | Opt into React Router v7 future flags | Medium | 0.5 | Not started |  | Clears dev warnings; avoids breaking upgrade later
5 | A | Tag a known-good baseline commit | Medium | 0.25 | Not started |  | Clean rollback point before feature work
6 | B | Validate EXP guardrail (never primary switcher) | High | 0.5 | Not started |  | EXP only for splitting / HDMI / local lectern switch
7 | B | Prove product-selection variety across scenarios | High | 1 | Not started |  | Engine must not default to same SKU on similar I/O
8 | B | Verify room-type & vertical differentiation | High | 1 | Not started |  | Corp/Edu/Gov/Hospitality, size, multi-screen, IP vs cable
9 | B | Surface UC caveats in output (Zoom-cert, not Teams-cert) | Medium | 0.5 | Not started |  | Teams MTRs must be tested before install
10 | B | Re-run product index + data-source audits; fix encoding | Medium | 0.5 | Not started |  | Resolve UTF-8 issues in template/product data
11 | B | Spot-check 6-8 representative BOMs for accuracy | High | 1 | Not started |  | Include 'by others' rows + signal-path assumptions
12 | C | GURU: works for guest + signed-in users | High | 1 | Not started |  | Tool and marketing demo; no silent mock fallback
13 | C | GURU: call-notes / transcript interpretation solid | Medium | 0.5 | Not started |  | Handles pasted transcripts and notes
14 | C | Compare: honest pros/cons + reliable match engine | High | 1 | Not started |  | Investigative, evidence-backed, graceful on no-match
15 | C | Proposal: Discovery->Proposal produces customer-ready doc | High | 1.5 | Not started |  | Full flow end to end without dev intervention
16 | C | Diagrams: connectivity/schematic incl. multi-display & IP | High | 1 | Not started |  | Visual Studio + Videowall export quality reviewed
17 | C | UI polish: validation, skeletons, voice keyboard support | Medium | 1 | Not started |  | Extend validation to all input-heavy pages
18 | D | Provision Supabase project; apply schema migration | High | 0.5 | Not started |  | DECISION NEEDED: confirm Supabase vs Postgres
19 | D | Migrate file-store data to Supabase; verify integrity | High | 1 | Not started |  | Keep file backup; test concurrent use
20 | D | Set WINGMAN_STORAGE_MODE=supabase; exercise live | High | 0.5 | Not started |  | Confirm no data loss under load
21 | D | Move all secrets to host secret manager | High | 0.5 | Not started |  | Gemini, Google CSE, Supabase service-role key
22 | D | Health checks, structured logging, monitoring/alerting | High | 1 | Not started |  | Uptime + error-rate alerts
23 | D | Provision hosting, domain, TLS; deploy to staging | High | 1 | Not started |  | DECISION NEEDED: hosting target
24 | D | Run load test against staging | Medium | 0.5 | Not started |  | Confirm target concurrency held
25 | E | Add CSRF protection for state-changing requests | High | 0.5 | Not started |  | Currently SameSite-cookie only
26 | E | Document API-key rotation in OPERATIONS.md | Medium | 0.5 | Not started |  | Rotation procedure for all keys
27 | E | Full security review with HTTPS enforced | High | 1 | Not started |  | No high-severity findings open at launch
28 | E | Decide SSO/OAuth: launch or fast-follow | Medium | 0.25 | Not started |  | DECISION NEEDED: auth scope
29 | F | Soap-test standard designs in a workshop | High | 1 | Not started |  | Per WyreStorm rule: workshop-test before install
30 | F | UAT with 2-3 salespeople on full journey | High | 1 | Not started |  | Discovery -> Proposal sign-off
31 | F | Finish operator docs + rollback procedure | Medium | 0.5 | Not started |  | README, DEPLOYMENT, OPERATIONS runbooks
32 | F | Final verify + load test; production deploy; go/no-go | High | 0.5 | Not started |  | Against success criteria
|  | Total estimated effort (days) |  | 23.5

## Dashboard
Progress Dashboard
Status | Count
Done | 0
In progress | 0
Blocked | 0
Not started | 32
Total tasks | 32
% complete | 0%
By phase
Phase | Tasks | Done | Effort (days)
A — Stabilise & prove build | 5 | 0 | 2.75
B — Data & selection accuracy | 6 | 0 | 4.5
C — Feature completion | 6 | 0 | 6
D — Production infrastructure | 7 | 0 | 5
E — Security & compliance | 4 | 0 | 2.25
F — Launch | 4 | 0 | 3

## Decisions
Decisions Needed From Steve
Decision | Why it matters / options | Your call
Production hosting | Where app + API run (container host / VPS / cloud). Sets deploy target & TLS.
Database | Confirm Supabase (recommended, already coded) vs self-managed Postgres.
Auth scope for launch | Email/password only, or add SSO/OAuth? Affects Phase E.
Gemini / search keys | Confirm production API keys & quotas for GURU and competitor search.
Launch audience | Internal sales first, or external customers? Sets security/UAT bar.